**IT Project Management**

**Microsoft project Exercise**

**You are the project manager of a Database development project for your customers’ data. This database will be used later in the CRM system.**

|  |  |  |
| --- | --- | --- |
| Project Tasks | Task Duration | Resources |
| **Design the database** |  | Project manager |
| Identify entities | 2 days | Designer |
| Identify attributes | 3 days | Designer |
| Build the database | 5 days | Developer, Microsoft Access |
| Database complete | 0 days |  |
| Prepare the data | 2 days | End user |
| Enter the data | 3 days | End User |

**The tasks should be in this order:**

Identifying the attributes occurs after identifying the entities.

Building the database occurs after finishing designing the database.

The database is considered complete when “build the database” task finished.

Prepare the data can start with the start of building the database.

Entering the data cannot occur before completing the database and preparing the data.

**Plan this project using MS project and view:**

* Gantt chart
* Resource graph